## Sheet1
MFR Project Schedule
Due Dates
|  | 2014-11-07 | 2014-11-14 | 2014-11-21 | 2014-11-28 | 2014-12-05 | 2014-12-09 | 2014-12-11 | 2014-12-12
Tasks | Read Documentation & Meet with Professors | bar: 2014-11-07
Obstacle Map with Initial and End Goals | bar: 2014-11-14
Plan & Plot the Optimal Path with Gradient Descent | bar: 2014-11-14 to 2014-11-21
Plan & Plot the Optimal Path with Shadow Traverse | bar: 2014-11-21 to 2014-12-05
Compare Costs (Time, Resources, Distance, etc) | bar: 2014-11-28 to 2014-12-05
Attend Presentations | bar: 2014-12-09 to 2014-12-12
Report Due Date* | bar: 2014-12-12
*Report due on Dec 12 by 8:30 PM. Email to professors as a PDF.